## Roadmap
Project Goal: Launch a new company website to increase online presence and improve customer engagement.
Milestone | Outcomes | Success Metric: | Timeframe | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
1. Market Research and Planning | Understand user needs and define website requirements. | Completion of user surveys and market analysis report. | January - February | bar: Jan to Feb
2. Design Phase | Create a user-friendly and visually appealing website design. | Approval of wireframes and design mockups. | February - March | bar: Feb to Mar
3. Development Phase | Develop the website with all required features and functionalities. | Completion of website development and internal testing. | March-April | bar: Mar to Apr
4. Content Creation | Develop and integrate high-quality content for the website. | Approval of all website content. | March - April | bar: Mar to Apr
5. Testing and Quality Assurance | Ensure the website is bug-free and performs well. | Successful completion of beta testing with no critical issues. | April - May | bar: Apr to May
6. Launch and Marketing | Successfully launch the website and drive initial traffic. | Achieve 10,000 unique visitors in the first month. | May- June | bar: May to Jun

## Gantt chart
[7 empty] | J A N U A R Y | [30 empty] | F E B R U A R Y | [27 empty] | M A R C H | [30 empty] | A P R I L | [29 empty] | M A Y | [30 empty] | J U N E
Ref | Milestones/Tasks | Start Date | End Date | Duration (days) | Team | Dependencies | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | [5 empty] | Milestone
2 | [5 empty] | Milestone
3 | [5 empty] | Milestone
4 | [5 empty] | Milestone
5 | [5 empty] | Milestone
6 | [5 empty] | Milestone