## Requirements
Feature | Req ID | Requirements
Contact Management | REQ_01 | Enable sales representatives to list, view, add, edit, and delete customer contacts. Contact details must include customer name, company name, email, phone, additional details.
| REQ_02 | Allow users to import and export contact lists.
Sales Opportunity Tracking | REQ_03 | Implement functionality for users to create and update sales opportunities.
| REQ_04 | Implement dashboard analytics to track opportunities through different stages of the sales cycle.
Reporting and Analytics | REQ_05 | Generate reports on sales performance.
| REQ_06 | Provide dashboard analytics to visualize sales data.
Integration and Automation | REQ_07 | Integrate the CRM with email and calendar systems.
| REQ_08 | Automate reminders and follow-up tasks for sales representatives.
System Performance NFRs | REQ_09 | The system should be able to handle at least 500 concurrent users without any degradation in performance.
| REQ_10 | Page load times for any CRM feature must not exceed 3 seconds under normal network conditions.

## EPICS
Feature | US_ID | EPIC
Contact Management | US_01
Sales Opportunity Tracking | US_02
Reporting and Analytics | US_03 | As a Sales Manager, I want to view dashboard analytics and sales reports to gain insights into team performance and customer interactions. Acceptance criteria: - Sales Managers can view dashboard analytics that show team performance and customer interactions - Sales Managers can generate and download sales reports.
Integration and Automation | US_04

## User Stories
ID | User Story Title | User Story Description | Relates to Epic | Acc_ID | Acceptance Criteria
US-05 | List Customer Contacts |  | US_01 | US-05-01
US-05-02
US-05-03
US-05-04
US-06
US-07
US-08
US-09
US-10
US-11
US-12
US-13
US-14
US-15

## Roadmap
ID | Phase/Key Milestone | Duration | Week _01 | Week _02 | Week _03 | Week _04 | Week _05 | Week _06 | Week _07 | Week _08 | Week _09 | Week _10 | Week _11 | Week _12 | Week _13 | Week _14 | Week _15 | Week _16 | Week _17
1 | Contact Management: Sales representatives can manage customer contacts easily. | 20 days
2 | Sales Opportunity Tracking: Users can track sales opportunities and update their status. | 10 days
3 | Reporting and Analytics: Sales managers can gain insights into team performance and customer interactions. | 30 days
4 | Integration and Automation: CRM integrated with Outlook email & calendar, sales staff receive automated reminders about meetings and tasks | 20 days
5 | Project Closure | 1 day
| Total | 81 days

## Gantt Chart
| Project : | Resource | Duration | Start | End | Sprint 1 | [13 empty] | Sprint 2 | [13 empty] | Sprint 3 | [13 empty] | Sprint 4 | [13 empty] | Sprint 5 | [13 empty] | Sprint 6 | [13 empty] | Sprint 7 | [13 empty] | Sprint 7
Ref | Phase, User Story/Task | Role or person | Days | Date | Date | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14

## Traceability Matrix
Feature/ | Req ID | Requirements | User Story IDs | Task IDs | TEST Ids | Test Execution notes
Contact Management | REQ_01 | Enable sales representatives to list, view, add, edit, and delete customer contacts. Contact details must include customer name, company name, email, phone, additional details.
| REQ_02 | Allow users to import and export contact lists.
Sales Opportunity Tracking | REQ_03 | Implement functionality for users to create and update sales opportunities.
| REQ_04 | Provide a visual sales pipeline to track opportunities through different stages of the sales cycle.
Reporting and Analytics | REQ_05 | Generate reports on sales performance and customer interactions.
| REQ_06 | Provide dashboard analytics to visualize sales data.
Integration and Automation | REQ_07 | Integrate the CRM with email and calendar systems.
| REQ_08 | Automate reminders and follow-up tasks for sales representatives.
System Performance | NFR_01 | The system should be able to handle at least 500 concurrent users without any degradation in performance.
| NFR_01 | Page load times for any CRM feature must not exceed 3 seconds under normal network conditions.